Restaurant Website

Implementation Plan & Complete Developer Guide

Version 1.0  |  March 2026

# 1. Tech Stack Assessment

Before diving into implementation, here is an honest evaluation of the proposed technology choices for your restaurant website.

Verdict: The Stack Is Suitable with Minor Recommendations

React (Frontend): EXCELLENT choice. Component-based, fast, great ecosystem, easy to find developers.

Flask vs Django: Recommendation is Flask for simplicity. Django is heavier and overkill for this project.

SQLite: Suitable for low-to-medium traffic (under ~500 concurrent users). Easy to migrate to PostgreSQL later.

Free Hosting: Render.com (recommended) offers free tier for both React frontend and Flask backend.

Overall: This stack is beginner-friendly, well-documented, and production-ready for a restaurant website.

## 1.1 Detailed Stack Comparison

| Technology | Assessment & Notes |
| --- | --- |
| React (Frontend) | Best choice. Large community, reusable components, fast rendering. Use Vite as the build tool (faster than Create React App). |
| Flask (Backend) | Recommended over Django. Lightweight, less boilerplate, perfect for a REST API. Easy to learn and deploy. |
| Django (Alternative) | More built-in features but overkill here. Use only if you need Django Admin panel for a non-technical admin. |
| SQLite (Database) | Good for development and low-traffic production. File-based, zero config. Easily upgradeable to PostgreSQL later. |
| Render.com (Hosting) | Best free tier for this stack. Hosts React (static) + Flask (web service) + SQLite. Free tier spins down after inactivity. |
| Cloudinary (Images) | Free tier (25GB) for storing dish images. Do NOT store images in SQLite or the server filesystem. |

# 2. Project Overview

## 2.1 Website Pages & Features

| Page | Features |
| --- | --- |
| Home / Landing | Restaurant banner, featured dishes, short intro, hours & location, CTA buttons |
| Menu | All dishes by category (Starters, Mains, Desserts, Drinks), each with image, name, description, price |
| Special Items | Featured/seasonal dishes with larger cards, detailed view with full description and nutritional info |
| Dish Detail Page | Full-page view for any dish: large image, full description, ingredients, price, allergen info |
| Contact Us | Restaurant address, phone, email, map embed, operating hours, inquiry form |
| Admin Panel | Secure login, add/edit/delete dishes, upload images, toggle dish availability, mark as special |

## 2.2 Database Schema (SQLite)

| Table | Columns & Purpose |
| --- | --- |
| dishes | id, name, description, price, category, image_url, is_available, is_special, created_at, updated_at |
| categories | id, name, display_order (e.g., Starters, Mains, Desserts, Drinks) |
| admin_users | id, username, password_hash, created_at (bcrypt hashed passwords only) |
| contact_messages | id, name, email, phone, message, created_at (stores contact form submissions) |

# 3. Implementation Phases

## 3.1 Phase Timeline Overview

| Phase | Duration | Tasks | Deliverable |
| --- | --- | --- | --- |
| Phase 1 | Week 1 | Project setup, folder structure, environment config, GitHub repo | Running dev environment |
| Phase 2 | Week 2 | Backend: Flask API, SQLite models, all REST endpoints, admin auth | Working API (test with Postman) |
| Phase 3 | Week 3 | Frontend: React setup, routing, Menu page, Dish Detail page | Menu browsing working |
| Phase 4 | Week 4 | Frontend: Special Items, Contact page, Home page, styling | All public pages done |
| Phase 5 | Week 5 | Admin panel: login, CRUD for dishes, image upload via Cloudinary | Fully functional admin |
| Phase 6 | Week 6 | Testing, bug fixes, performance optimization, mobile responsiveness | QA-approved build |
| Phase 7 | Week 7 | Deployment to Render.com, domain setup, handover documentation | Live website + docs |

## 3.2 Phase 1: Project Setup (Week 1)

### Step 1 - Create Project Structure

Create the following folder structure for the entire project:

restaurant-website/
  backend/           (Flask app)
  frontend/          (React app)
  docs/              (Documentation)
  .github/           (GitHub Actions for CI/CD)

### Step 2 - Initialize Git Repository

- Create a new GitHub repository (free at github.com)

- Run: git init, git remote add origin <your-repo-url>

- Create a .gitignore for Python (venv, __pycache__) and Node (node_modules)

### Step 3 - Backend Setup (Flask)

- Install Python 3.11+ from python.org

- Create virtual environment: python -m venv venv

- Activate: source venv/bin/activate (Mac/Linux) or venv\Scripts\activate (Windows)

- Install packages: pip install flask flask-sqlalchemy flask-cors flask-jwt-extended cloudinary python-dotenv bcrypt

- Create backend/requirements.txt: pip freeze > requirements.txt

### Step 4 - Frontend Setup (React + Vite)

- Install Node.js 18+ from nodejs.org

- Run: npm create vite@latest frontend -- --template react

- Install dependencies: npm install react-router-dom axios

- Install styling: npm install tailwindcss @tailwindcss/vite (or use plain CSS)

## 3.3 Phase 2: Backend API (Week 2)

### Flask App Structure

| File | Purpose |
| --- | --- |
| backend/app.py | Main Flask application entry point, app factory |
| backend/models.py | SQLAlchemy models: Dish, Category, AdminUser, ContactMessage |
| backend/routes/dishes.py | GET /api/dishes, GET /api/dishes/:id, GET /api/specials |
| backend/routes/admin.py | POST /api/admin/login, POST/PUT/DELETE /api/admin/dishes |
| backend/routes/contact.py | POST /api/contact (save contact form submission) |
| backend/config.py | Configuration: database URL, JWT secret, Cloudinary keys |
| backend/.env | Environment variables (never commit to GitHub) |

### Key API Endpoints

| Endpoint | Description |
| --- | --- |
| GET /api/dishes | Returns all available dishes. Query param: ?category=Mains |
| GET /api/dishes/:id | Returns single dish with full details |
| GET /api/dishes/specials | Returns all dishes marked as special |
| GET /api/categories | Returns all menu categories |
| POST /api/contact | Saves a contact form message to database |
| POST /api/admin/login | Admin login, returns JWT token |
| POST /api/admin/dishes | Create new dish (requires JWT auth header) |
| PUT /api/admin/dishes/:id | Update dish details or toggle availability (requires JWT) |
| DELETE /api/admin/dishes/:id | Delete a dish permanently (requires JWT) |
| POST /api/admin/upload | Upload dish image to Cloudinary, returns image URL |

## 3.4 Phase 3-4: Frontend (Weeks 3-4)

### React Component Architecture

| Component/Page | Description |
| --- | --- |
| App.jsx | Root component, React Router setup with all routes |
| components/Navbar.jsx | Navigation bar with links to all pages, mobile hamburger menu |
| components/DishCard.jsx | Reusable card showing dish image, name, price. Used on Menu + Specials pages |
| pages/Home.jsx | Landing page with hero banner, featured dishes, restaurant info |
| pages/Menu.jsx | Full menu with category tabs/filters, grid of DishCards |
| pages/DishDetail.jsx | Individual dish page at /dish/:id with full info |
| pages/Specials.jsx | Special items page with enhanced display cards |
| pages/Contact.jsx | Contact form + restaurant info + embedded Google Map |
| pages/admin/AdminLogin.jsx | Admin login form, stores JWT in memory/sessionStorage |
| pages/admin/AdminDashboard.jsx | Admin home: list all dishes with edit/delete buttons |
| pages/admin/AdminDishForm.jsx | Form to add or edit a dish with image upload |

### React Router Setup

| Route | Component |
| --- | --- |
| / | Home.jsx |
| /menu | Menu.jsx |
| /menu/:id | DishDetail.jsx |
| /specials | Specials.jsx |
| /contact | Contact.jsx |
| /admin/login | AdminLogin.jsx |
| /admin/dashboard | AdminDashboard.jsx (protected route) |
| /admin/dishes/new | AdminDishForm.jsx (add mode) |
| /admin/dishes/:id/edit | AdminDishForm.jsx (edit mode) |

## 3.5 Phase 5: Admin Panel (Week 5)

The admin panel allows the restaurant owner to manage dishes daily without any coding.

### Admin Features

- Username + password with JWT token authentication: Secure Login

- Form with name, description, price, category, image upload, mark as special: Add Dish

- Pre-filled form with all existing dish data, update any field: Edit Dish

- Confirmation dialog before permanent deletion: Delete Dish

- One-click switch to show/hide a dish without deleting it: Toggle Availability

- Toggle to feature a dish on the Specials page: Mark as Special

- Direct upload to Cloudinary, image URL saved in database: Image Upload

### Security Implementation

- Passwords stored as bcrypt hashes (never plain text)

- JWT tokens expire after 8 hours, requiring re-login

- All admin API endpoints require valid JWT in Authorization header

- Frontend stores JWT in memory (not localStorage) for better security

- CORS configured to only allow requests from your frontend domain

# 4. Deployment Guide (Render.com - Free Tier)

## 4.1 Why Render.com

| Feature | Details |
| --- | --- |
| Frontend (React) | Static Site hosting - 100% free, no expiry, global CDN |
| Backend (Flask) | Web Service - Free tier, spins down after 15 min inactivity (cold start ~30 sec) |
| Database | SQLite file stored on the server. Note: Render free tier disk is ephemeral. Use Render Disk addon ($7/mo) or switch to Render PostgreSQL (free 90 days) for persistence |
| Custom Domain | Free SSL certificate included for any custom domain |
| Upgrade Path | Paid tier starts at $7/month when you need always-on backend |

## 4.2 Step-by-Step Deployment

### Deploy Backend (Flask) to Render

- Push your code to GitHub

- Go to render.com and sign up with GitHub

- Click New > Web Service, connect your GitHub repo

- Set Root Directory to: backend

- Set Build Command: pip install -r requirements.txt

- Set Start Command: gunicorn app:app (add gunicorn to requirements.txt)

- Add Environment Variables: DATABASE_URL, JWT_SECRET_KEY, CLOUDINARY_URL

- Click Deploy. Your API will be at: https://your-app.onrender.com

### Deploy Frontend (React) to Render

- Click New > Static Site, connect same GitHub repo

- Set Root Directory to: frontend

- Set Build Command: npm install && npm run build

- Set Publish Directory: dist

- Add Environment Variable: VITE_API_URL=https://your-backend.onrender.com

- Click Deploy. Your site will be at: https://your-app-frontend.onrender.com

### Connect Custom Domain (Optional)

- Buy a domain from Namecheap or GoDaddy (~$10-15/year)

- In Render, go to your Static Site > Settings > Custom Domain

- Add your domain and follow the DNS configuration instructions

- Render provides free SSL/HTTPS automatically

# 5. Project Handover Checklist

## 5.1 Code Handover

- GitHub repository access transferred to client (add as Owner)

- All environment variables documented in a secure password manager

- README.md with setup instructions in the repository root

- requirements.txt and package.json are up to date

- No hardcoded secrets or API keys in the codebase

## 5.2 Hosting Handover

- Render.com account credentials transferred to client

- Cloudinary account credentials transferred to client

- Custom domain DNS credentials transferred (if applicable)

- Automatic deployments from GitHub main branch confirmed working

## 5.3 Admin Panel Training

- Record a 10-15 minute Loom video showing: login, add dish, edit dish, delete dish, mark as special

- Provide written step-by-step admin guide (simple language, with screenshots)

- Do a live walkthrough session with the restaurant owner

- Create a test dish together during training so they are comfortable

## 5.4 Documentation Provided

- SRS Document (Software Requirements Specification)

- Implementation Plan (this document)

- Admin User Manual

- API Documentation (list of all endpoints)

- Deployment & Maintenance Guide

# 6. Post-Launch Maintenance

## 6.1 Regular Tasks

| Frequency | Task |
| --- | --- |
| Daily | Check the website loads correctly, verify admin panel works |
| Weekly | Review contact form submissions in the database |
| Monthly | Check Cloudinary storage usage (free: 25GB) |
| Quarterly | Update Python and npm packages for security patches |
| Annually | Renew domain name, review hosting plan needs |

## 6.2 Common Issues & Fixes

| Issue | Solution |
| --- | --- |
| Backend slow to respond (cold start) | Normal on free Render tier. Upgrade to paid ($7/mo) for always-on service |
| Image not showing | Check Cloudinary URL is correct in database, verify Cloudinary account is active |
| Admin login not working | Check JWT_SECRET_KEY environment variable is set in Render |
| Database data lost after redeploy | Free Render disk is ephemeral. Add Render Disk addon or migrate to PostgreSQL |
| CORS errors in browser | Verify frontend domain is in Flask CORS allowed origins list |

End of Implementation Plan